## SprintInfo
Start Date | 2019-03-22 | Enter the start date for the sprint
End Date | 2019-04-20 | Enter the ending date for the sprint
Elapsed Days | 21
Holidays | 0 | If there are any holidays or other special days occuring during the sprint, enter that number here
Working Days | 21
Number of Devs | 4
Utilization | 15% | Enter a value for the utilization of the team
Available Dev Hours | 100.8
Daily Dev Hours | 4.8

## BacklogTable
Sprint | Item ID | Estimated Hours | Task Name | Assigned To | Remaining Hours | Status | Actual hours
| 1 | 4 | Ibanity API study | rovherck | 0 | Completed | 4
| 2 | 4 | Login flow | jgdevreke | 0 | Completed | 8
| 3 | 2 | Stock Page | rodproft | 0 | Completed | 7
| 4 | 3 | Tab transactions | jgdevreke | 0 | Completed | 5
| 5 | 2 | Home Page | arbertra | 0 | Completed | 5
| 6 | 2 | Money Page | rodproft | 0 | Completed | 7
| 7 | 3 | Account Page | rovherck | 1 | In Progress | 3
| 8 | 6 | Shopping basket | arbertra | 1 | In Progress | 14
| 9 | 3 | TAB/TAP api extensions | arbertra | 1 | In Progress | 4
| 10 | 4 | TAB/TAP api manager | jgdevreke | 2 | In Progress | 6
| 11 | 3 | Navbar | rodproft | 0 | Completed | 5
| 12 | 4 | History Page | rodproft | 3 | In Progress | 4
| 13 | 3 | Permission management | jgdevreke | 0 | Completed
Total |  | 43 |  |  | 8 |  | 72

## BurnDownTable
Work Day | Target Burn Down | Forecast Burn Down | Actual Burn Down
0 | 43 | 43 | 43 | 2019-03-22
1 | 40.9524 | 38.2 | 43 | 2019-03-23
2 | 38.9048 | 33.4 | 43 | 2019-03-24
3 | 36.8571 | 28.6 | 43 | 2019-03-25
4 | 34.8095 | 23.8 | 43 | 2019-03-26
5 | 32.7619 | 19 | 43 | 2019-03-27
6 | 30.7143 | 14.2 | 43 | 2019-03-28
7 | 28.6667 | 9.4 | 43 | 2019-03-29
8 | 26.619 | 4.6 | 40 | 2019-03-30
9 | 24.5714 | -0.2 | 35 | 2019-03-31
10 | 22.5238 | -5 | 30 | 2019-04-01
11 | 20.4762 | -9.8 | 28 | 2019-04-02
12 | 18.4286 | -14.6 | 26 | 2019-04-03
13 | 16.381 | -19.4 | 25 | 2019-04-04
14 | 14.3333 | -24.2 | 19 | 2019-04-05
15 | 12.2857 | -29 | 19 | 2019-04-06
16 | 10.2381 | -33.8 | 19 | 2019-04-07
17 | 8.1905 | -38.6 | 16 | 2019-04-08
18 | 6.1429 | -43.4 | 15 | 2019-04-09
19 | 4.0952 | -48.2 | 10 | 2019-04-10
20 | 2.0476 | -53 | 8 | 2019-04-11
21 | 0 | -57.8 | 4 | 2019-04-12
Note on A2: PowerUps for Excel: Create one row per day in the sprint.