## SprintInfo
Start Date | 2019-03-22 | Enter the start date for the sprint
End Date | 2019-04-20 | Enter the ending date for the sprint
Elapsed Days | 21
Holidays | 0 | If there are any holidays or other special days occuring during the sprint, enter that number here
Working Days | 21
Number of Devs | 4
Utilization | 15% | Enter a value for the utilization of the team
Available Dev Hours | 100.8
Daily Dev Hours | 4.8

## BacklogTable
Sprint | Item ID | Estimated Hours | Task Name | Assigned To | Remaining Hours | Status
| 1 | 4 | Ibanity API study | rovherck | 0 | Completed
| 2 | 4 | Login flow | jgdevreke | 0 | Completed
| 3 | 2 | Stock Page | rodproft | 0 | Completed
| 4 | 3 | Tab transactions | jgdevreke | 0 | Completed
| 5 | 2 | Home Page | arbertra | 0 | Completed
| 6 | 2 | Money Page | rodproft | 0 | Completed
| 7 | 3 | Account Page | rovherck | 3
| 8 | 6 | Shopping basket | arbertra | 6
| 9 | 3 | TAB/TAP api extensions | arbertra | 3
| 10 | 4 | TAB/TAP api manager | jgdevreke | 4
| 11 | 3 | Permission management | jgdevreke | 3
Total |  | 36 |  |  | 19

## BurnDownTable
Work Day | Target Burn Down | Forecast Burn Down | Actual Burn Down
0 | 36 | 36 | 36 | 2019-03-22
1 | 34.2857 | 31.2 | 36 | 2019-03-23
2 | 32.5714 | 26.4 | 36 | 2019-03-24
3 | 30.8571 | 21.6 | 36 | 2019-03-25
4 | 29.1429 | 16.8 | 36 | 2019-03-26
5 | 27.4286 | 12 | 36 | 2019-03-27
6 | 25.7143 | 7.2 | 36 | 2019-03-28
7 | 24 | 2.4 | 36 | 2019-03-29
8 | 22.2857 | -2.4 | 36 | 2019-03-30
9 | 20.5714 | -7.2 | 36 | 2019-03-31
10 | 18.8571 | -12 | 30 | 2019-04-01
11 | 17.1429 | -16.8 | 28 | 2019-04-02
12 | 15.4286 | -21.6 | 26 | 2019-04-03
13 | 13.7143 | -26.4 | 25 | 2019-04-04
14 | 12 | -31.2 | 19 | 2019-04-05
15 | 10.2857 | -36 | 19 | 2019-04-06
16 | 8.5714 | -40.8 | 19 | 2019-04-07
17 | 6.8571 | -45.6 | 16 | 2019-04-08
18 | 5.1429 | -50.4 | 15 | 2019-04-09
19 | 3.4286 | -55.2 | 10 | 2019-04-10
20 | 1.7143 | -60 | 8 | 2019-04-11
21 | 0 | -64.8 | 0 | 2019-04-12
Note on A2: PowerUps for Excel: Create one row per day in the sprint.